**Report on the implemented activities of the project ‘Climate Heroes-Let’s save the planet’ from August 2020 to July 2021**

**27th August 2020**. –**dissemination activity**- Teachers’ Council and parents were informed about the project and its realization. The report about starting the project was sent to the Teachers’ Council on 14th September, 2020. The local community, Parents’ Council and the School Board were also informed about the activities and the realization of the project.

**12th November 2020.**-**project management activity** - The first online meeting via Google Meet was held . The meeting started at 4pm and finished at 4.45pm.

 **27th November 2020. workshops** -**school activity** -The topic of the workshops was ‘Climate Change and its impact on weather and nature’. All material from the two workshops was posted on e-Twinning ( photos, script ) . The report about them was also posted.

-Younger students -Workshops Climate Change and Greenhouse were done.

-associations which solution was Greenhouse.

-short check -What they learned about climate change ?

-Older students -The presentation, the report and the script from the workshop , as well as photos, were posted on e-Twinning on 27th November 2020.

-The associations from the workshop were posted on e-Twinning.

- A short film about our school and also the presentations about Serbia and our city -Kragujevac were posted ,too.

-**14th December 2020.** via Google Meet -**project management activity-** a meeting of the Project Implementation Team was held.

**-18th December 2020.-dissemination activity -**Two reports on the workshops were written and sent to the Teachers’ Council , the Parents’ Council and the School Board.

**20th December .2020. -dissemination activity** -Team members created a special site and linked it to the school site so that everyone would have the opportunity to see the implemented activities within the project.  **<http://www.os-vukstkaradzic.edu.rs/>**

**<https://sacuvajmoplanetu.weebly.com/>**

**23rd February 2021.-school activity** -Logo proposal

**23rd February -27th March -school activity -**A poll for the selection of the logo was conducted. After the voting the final table was made and the Lithuanian logo proposal was chosen.

**March 2021.-dissemination activity-**Our project was presented through a blog to the Association of Physicists of Sumadija. **<http://fizicrisumadije.blogspot.com/2020/12/blog-post.html?m=1>**

**23rd March 2021.-school activity**- Students and Team members made welcome packets for our partners. **30th March 2021-project management activity-** Photos of welcome packets and the report from the workshops were posted on e-Twinning.

-The final voting table of the students of our school for the choice of the logo was set up.

**13th April 2021.-project management activity**- The meeting online with our project partners was held via Google Meet. It started at 5pm and ended at 6pm.

**22ndApril .2021.-school activity**-Older students-Earth Day presentation was held by the 6th grade students to younger students ( 4th grade students ) in English.

Younger students - The topic -**Your care about the planet**

The problems they talked about were : **Protection of endangered species, Collection of raw materials for recycling , Air protection from pollution from factory and other chimneys , the issue of sewage and other wastewater.**

The English teacher held two classes dedicated to the celebration of Earth Day with 1st and 2nd grade students .

**23rd April 2021**.- **project management activity-** The presentation altogether with lesson plans and photos were posted on e-Twinning.

**May and June 2021**.-**project management activity**-All Team members except the English teacher attended an English language course at the private Master Center school.

**4th May 2021**.-**school activity**-Workshops with students who designed a costume on the topic of climate change were held .

**7th June 2021**.-**school activity** -The dictionary of Climate change was filled with Serbian words .

**9th June .2021.-school activity -**A survey was conducted - 8 costumes were selected. The students voted for the most beautiful costume. We also found and consulted a fashion designer , who helped the students to design the costume.

**7th July 2021**.-**project management activity -** The costume proposal was posted on e-Twinning.

**Until 9th June 2021**. –**project management activity** -A total of 7 meetings of the members of the Project Implementation Team were held. All meeting reports can be found on our website.

 **The report written by the Team coordinator , Vesna Dimitrijević Translation by Zorica Petrović, the English teacher**